## Action
How to evaluate porting of a driver
No. | Action
Step 1 | Check Hardware
Step 2 | Check module source code
Step 3 | List porting points (Base on the AD, DD of module and result of step 2)
Step 4 | Write detail description(If needed)
Step 5 | Evaluate Porting difficulty
Step 6 | Estimate Porting time

## Porting Estimation
Porting Estimation
Porting difficulty Table
Complexity | Description |  | Difficulty
1 | Only copy code, fix kernel config,… |  | Easy
2 | Fix small hardware change |  | Medium
Copy code, complile error
3 | Fix big hardware change |  | Hard
Fix flow change
4 | Can not reuse code |  | Very hard
No | Module | SubModule | Source location(*) | Content of change | Detail Description | How to port/implement | Complexity | Duration (Days) | [5 empty] | Note
[8 empty] | Porting | FMEA | Design spec | UT | IT | Total
1 | RTC | _ | bsp/kernel/drivers/char/jk_rtc | Fix i2c channel address | I2C channel is change from …(I2C source location) |  | 2: Medium | 0.5 | TBD | TBD | TBD | TBD | TBD | _
|  |  |  | Port RTC driver | _ |  | 2: Medium | 2 | TBD | TBD | TBD | TBD | TBD | _
2 | Video | fbdev | bsp/kernel/drivers/video/fbdev/tcc/tcc_vioc_fb.c bsp/kernel/drivers/video/fbdev/tcc/jk_fb.c bsp/kernel/drivers/video/fbdev/tcc/jk_lcd.c bsp/kernel/drivers/video/fbdev/core/* | Add support for FB1 | _ |  | 3: Hard | 5 | TBD | TBD | TBD | TBD | TBD | _
|  |  |  | Add support for IQA | _ |  | 2: Medium | 1 | TBD | TBD | TBD | TBD | TBD | _
|  |  |  | Fix memory leak at driver initialization | _ |  | 1: Easy | 0.5 | TBD | TBD | TBD | TBD | TBD | _
|  |  |  | Support for HDMI rear monitor output | Old source code does not support HDMI output |  | 4: Very hard | TBD | TBD | TBD | TBD | TBD | TBD | _
Note
(*): Location of driver in old source code(azalea_r1760)