## Action
How to evaluate porting of a driver
No. | Action
Step 1 | Check Hardware
Step 2 | Check module source code
Step 3 | List porting points (Base on the AD, DD of module and result of step 2)
Step 4 | Write detail description(If needed)
Step 5 | Evaluate Porting difficulty
Step 6 | Estimate Porting time

## Porting Estimation
Porting Estimation
Porting difficulty Table
Complexity |  | Description |  | Difficulty
1 |  | Only copy code, fix kernel config, or fix compile, … |  | Easy
2 |  | Fix small hardware change |  | Medium
Copy code, complile error
3 |  | Fix big hardware change |  | Hard
Fix flow change
4 |  | Can not reuse code |  | Very hard
No | Development requirement | Module | SubModule | Source location(*) | Content of change | Detail Description | How to port/development | Porting/Develop Type | Complexity | Duration (Days) | [5 empty] | Status | Note
[10 empty] | Porting/Development | FMEA | Updating Design spec | Design testing |  | Total
[13 empty] | UT | IT
1 | Drivers (in Kernel) | MscDev | _ | bsp/kernel/drivers/mscdev/ | - Fix hardware interface change | GPSB and control signal of Panelcom and Maincom change | - Correct GPIO control. - Correct GPSB channel, and Interrupt, DMA channel. - Update dts | Porting | 2: Medium | 6 | TBD | TBD | TBD | TBD | TBD | Done | _
2 |  | TMC | _ | bsp/kernel/drivers/jktmc/ | - Fix hardware interface change - i2c_driver struct change | - I2C channel, base address, INT, RST signal. - i2c_driver struct is changed by Kernel 4.x.x | - Correct I2C channel. - Correct INT, RST signal. - Correct resume() and resume() in jktmc_i2c_driver struct - Update dts | Porting | 2: Medium | 5 | TBD | TBD | TBD | TBD | TBD | Done | _
4 |  | Vics | _ | bsp/kernel/drivers/jkfmvics/ | - Fix hardware interface change | - SPI, base address, INT, RST signal change. | - Correct spi channel and RST, REQ, INT - Update dts | Porting | 2: Medium | 5 | [5 empty] | Done
5 |  | Antenna | _ | bsp/kernel/drivers/antenna/antenna.c bsp/kernel/drivers/antenna/antenna_dab.c | - Fix hardware interface change | - ANA_ON, ANA_DET, INT signal change | - Correct GPIO pin and - Update dts | Porting | 2: Medium | 4 |  |  | TBD | TBD | TBD | Done | _
6 |  | jkDummyKey | _ |  |  |  |  | Porting |  |  |  |  | TBD | TBD | TBD | InProgress | _
7 |  | jkDummyTouch | _ |  |  |  |  | Porting |  |  |  |  | TBD | TBD | TBD | InProgress | _
8 | Utility | libKernelFinalize | _ | jvckenwood/utilities/libKernelFinalize/ | - Compile error | Missing header file *.h | - Copy and correct header file *.h and Makefile | Porting | 1: Easy | 1 |  |  | TBD | TBD | TBD | Done | _
9 |  | openingcustomize | _ | jvckenwood/utilities/openingcustomize/ | - Compile error | Missing header file *.h | - Copy and correct header file *.h and Makefile | Porting | 1: Easy | 1 | [5 empty] | Done | _
10 |  | paniclog | _ | jvckenwood/utilities/paniclog/ | - Compile error | Missing header file *.h | - Copy and correct header file *.h and Makefile | Porting | 1: Easy | 1 | [5 empty] | Done | _
11 |  | surface_wrapper | _ | jvckenwood/utilities/surface_wrapper/ | - Compile error | Missing header file *.h | - Copy and correct header file *.h and Makefile | Porting | 1: Easy | 1 | [5 empty] | Done | _
12 | U-Boot (Cortex-A53) | U-boot starts rear camera | _ | - | - | - | - System init - VDEC setting - T-CON setting - Start early camera - Test + bug fixing | Built in | 4: Very hard | 10 | [5 empty] | Done | refer to pre-product
13 | Rear camera when starting (Running on Cortex-R5) | hw initialization | _ | - | - | - | - System-init - I2C driver communicate to Panelcom - GPIO control | Built in | 4: Very hard | 10 | [5 empty] | Done | refer to pre-product
14 |  | Rear camera display | _ | - | - | - | + Camera input - VDEC driver - R/F Camera control + Rear camera display - VIOC control - LCD control - Set image quality - Capture and stream | Built in | 4: Very hard | 12 | [5 empty] | Done | refer to pre-product
15 |  | Guide line display | _ | - | - | - | - Create guide line - Display guide line | Built in | 4: Very hard | 6 | [5 empty] | Done | refer to pre-product
16 |  | Panelcom communication | _ | - | - | - | - Panelcom driver - illumination setting | Built in | 4: Very hard | 4 | [5 empty] | Done | refer to pre-product
17 |  | Shift control to kernel driver | _ | - | - | - | - Communication between CR and CA | Built in | 4: Very hard | 4 | [5 empty] | Done | refer to pre-product
Note
(*): Location of driver in old source code(azalea_r1760)