## Task_Table
JLN2 detail schedule
Task | Duration | Start | Finish | Predecessors | Dependence | Notes
Rear camera at startup | 109 |  |  |  |  | Development based on client's spec
Documents | 26
FMEA | 16
Camera control in U-Boot | 3
Early camera software in Cortex-R5 | 11
Hardware system- initialization | 2
Camera input | 2
Rear camera display | 2
Guide line display | 2
Panelcom communication | 2
Shift camera control to kernel driver | 1
Review + update | 2
Updating design document | 10
System architecture design specification | 4
Software design specification | 4
Review + update | 2
Development & porting | 43
Camera control in U-Boot | 10
Camera system init | 2
VDEC setting | 2
T-CON setting | 2
Start early camera | 2
Test + bug fixing | 2
Early camera software in Cortex-R5 | 33
Hardware system- initialization | 5
System-init | 2
I2C driver | 1
Gpio control and other thing | 2
Camera input | 4
VDEC driver | 2
R/F Camera control | 2
Rear camera display | 8
VIOC control | 2
LCD control | 2
Set image quality | 2
Capture and stream | 2
Guide line display | 4
Create guide line | 2
Display guide line | 2
Panelcom communication | 4
panel com driver | 2
illumination setting | 2
Shift camera control to kernel driver | 2
Test + bug fixing | 6
Test design | 40
Test design spec | 8
Test plan spec | 1
Test case definition | 5
Review + update | 2
Execute testing | 27
Unit test implement (functional unit tests in the device driver for each modification part or development part) | 17
Camera functions in U-Boot | 3
Hardware system- initialization | 2
Camera input | 2
Rear camera display | 3
Guide line display | 2
Panelcom communication | 2
Shift camera control to kernel driver | 2
Guide line document | 1
Integration test (follow up functional requirement of Module) | 10
Execute testing | 10
Bug fixing | 5

## Resource_Table
JLN2 detail schedule
Task | Material Label | Group | Email Address | User Logon Account | Dependence | Standard Rate | Cost Per Use | Notes
Work | 106 |  |  |  |  | Development based on client's spec | 0
Work | 26 |  |  |  |  | $0.00/h | 0
Work | 16 |  |  |  |  | $0.00/h | 0
Work | 3 |  |  |  |  | $0.00/h | 0
Work | 11 |  |  |  |  | $0.00/h | 0
Work | 2 |  |  |  |  | $0.00/h | 0
Work | 2 |  |  |  |  | $0.00/h | 0
Work | 2 |  |  |  |  | $0.00/h | 0
2
2
1
Review + update | 2
10
4
4
Review + update | 2
43
10
2
VDEC setting | 2
2
2
Test + bug fixing | 2
33
5
2
1
2
4
2
2
8
2
2
2
2
4
2
2
4
2
2
2
Test + bug fixing | 6
Test design
Test spec
17
3
2
2
3
2
2
2
Review + update | 1
20
5
2
2
Review + update | 1
10
Bug fixing | 5

## Assignment_Table
JLN2 detail schedule
Task | Units | Dependence
| 106 |  | Development based on client's spec
26
16
3
11
2
2
2
2
2
1
Review + update | 2
10
4
4
Review + update | 2
43
10
2
VDEC setting | 2
2
2
Test + bug fixing | 2
33
5
2
1
2
4
2
2
8
2
2
2
2
4
2
2
4
2
2
2
Test + bug fixing | 6
Test design
Test spec
17
3
2
2
3
2
2
2
Review + update | 1
20
5
2
2
Review + update | 1
10
Bug fixing | 5